## Sheet1
ID | User Story | Story tasks | Sprint number | Sprint goal | Story type | Story Points | Story Points Completed | Names and Contribution Percentage
7 | As a registered user, I want to be able to appear offline so that I won't be disturbed. | Implement offline functionality to chatrooms | 4 | User will be offline in the chat when they leave the chatroom | F, T | 2 | 2 | Nick, 33%, Clark, 33%, Aidan, 33%
|  | Appear offline if app is closed | 4 | When user closes app, appear offline to friends | NF, T, KA | 1 | 0
|  | Code profile page for user | 4 | Allow user profiles. Show onine/offline status on profile page | F, T, KA | 2 | 1 | Nick, 33%. Clark, 33%. Aidan, 33%..
12 | As a registered user, I want to be able to view who’s online so that I know who I can chat with. | Design UI for friends list | 4 | Mock UI for friends tab | F, KA | 1 | 1 | Aidan, 20%. Clark, 20%. Stephen, 20%. Joe, 20%. Nick, 20%
|  | Implement adding friends | 4 | Allow user to add friends and show their online status | NF, T | 1 | 1 | Nick, 33%. Clark, 33%. Aidan, 33%.
|  | Implement online status of friends | 4 | Show user who's online on their friends list | F, T, KA | 1 | 0
8 | As a registered user, I want to be able to see a short list of users when I hover over a chat so that I can see if I know anyone. | Implement list showing chatroom occupants before joining | 4 | Show chatroom occupants by hovering over the chatroom | F, T | 2 | 2 | Nick, 50%. Clark, 50%.
|  | Implement list showing chatroom occupants after joining | 4 | show chatroom members / occupants after user joins chatroom | F, T | 1 | 1 | Nick, 50%. Clark, 50%.
9 | As a registered user, I want to receive chat notifications so that I can respond back promptly to friends. | Design UI for notifications | 4 | Show user a notification when a chats been updated | F, KA | 1 | 1 | Aidan, 20%. Clark, 20%. Stephen, 20%. Joe, 20%. Nick, 20%
|  | Implement notification UI | 4 | Add UI to notify user of chat updates | F, T | 1 | 1 | Nick, 50%. Clark, 50%.
|  | Implement in app notifications | 4 | Show user notifications for incoming chats or chatroom updates | NF, T, KA | 2 | 1 | Nick, 50%. Clark, 50%.
2 | As a registered user, I want to be able to include my interests in my profile so that like minded people can find me. | Design UI for interests on profile page | 4 | Mockup UI for interests | F, KA | 1 | 1 | Aidan, 20%. Clark, 20%. Stephen, 20%. Joe, 20%. Nick, 20%
|  | Code interests on profile page | 4 | Allow user to add interests to profile page | F, T | 1 | 1 | Nick, 50%. Clark, 50%
16 | As a registered user, I want to be able to visually see how big a chat room is so that I can avoid busy chat rooms. | Design UI for total users in a chatroom | 4 | Mockup UI for total users in a chatroom | F, KA | 1 | 1 | Aidan, 20%. Clark, 20%. Stephen, 20%. Joe, 20%. Nick, 20%
|  | Code total users in a chatroom | 4 | Show user how many users are in each chatroom. | F, T, | 1 | 1 | Nick, 100%
11 | As a registered user, I want to be able to send direct messages to other users so that I can chat with them in private. | Design UI for private chats | 4 | Mockup UI for private chatrooms with friends | F, KA | 1 | 1 | Aidan, 20%. Clark, 20%. Stephen, 20%. Joe, 20%. Nick, 20%
|  | Implement UI to start a private chat | 4 | Show private chat button on each friend in user friends list | F, T | 1 | 1 | Nick, 100%
|  | Code private chats with friends | 4 | Allow users to have a private chat with a friend | F, T | 2 | 2 | Nick, 50%. Clark, 50%
4 | As a registered user, I want to be able to add other users so that I can reach out to them in the future. | Design UI to add friends | 4 | Mockup UI to add friends via their profile | F, KA | 1 | 1 | Aidan, 20%. Clark, 20%. Stephen, 20%. Joe, 20%. Nick, 20%
|  | Implement add friend button to profile | 4 | Allow user to add friend when viewing their profile | F, T | 1 | 1 | Nick, 33%. Clark, 33%, Aidan, 33%.
|  | Implement add friend functionality | 4 | Allow user to send and recieve friend requests | NF, T | 3 | 3 | Nick, 100%.