## Sheet1
ID | User Story | Sprint Number | Story Priority | Story Status | Story Points
15 | As a registered user, I want to be able to logout of my account at any time so that I can keep my messages secure. | 2 | H | D | 6
1 | As an unregistered user, I want to be able to view chat rooms near me so that I can talk to people in my community. | 2 | M | IP | 8
3 | As a registered user, I want to be able to create my own chat room so that I can talk with friends in private. | 2 | H | T | 10
7 | As a registered user, I want to be able to appear offline so that I won't be disturbed. | 2 | L | IP | 5
14 | As a registered user, I want to be notified when a new user joins the chat so that I can greet them. | 2 | L | IP | 4
2 | As a registered user, I want to be able to include my interests in my profile so that like minded people can find me. | 3 | L | W | 2
4 | As a registered user, I want to be able to add other users so that I can reach out to them in the future. | 3 | L | W | 1
5 | As a registered user, I want the ability to delete previous messages that I sent in the case that I mistakenly write to the wrong chat. | 3 | M | W | 1
9 | As a registered user, I want to receive chat notifications so that I can respond back promptly to friends. | 3 | H | W | 3
10 | As a registered user, I want to be able to paste GIFs in chat so that I can reference funny memes. | 3 | L | W | 1
16 | As a registered user, I want to be able to visually see how big a chat room is so that I can avoid busy chat rooms. | 3 | M | W | 2
6 | As a registered user, I want to be able to filter my search for chat rooms by using keywords so that I can find where I belong. | 4 | H | W | 2
8 | As a registered user, I want to be able to see a short list of users when I hover over a chat so that I can see if I know anyone. | 4 | M | W | 2
11 | As a registered user, I want to be able to send direct messages to other users so that I can chat with them in private. | 4 | H | W | 4
12 | As a registered user, I want to be able to view who’s online so that I know who I can chat with. | 4 | M | W | 3
13 | As a registered user, I want to be able to set language filters for my chat rooms so that I can limit explicit language. | 4 | L | W | 1