## Sheet1
ID | User Story | Story tasks | Sprint number | Sprint goal | Story type | Story Points | Story Points Completed | Names and Contribution Percentage
3 | As a registered user, I want to be able to create my own chat room so that I can talk with friends in private. | Implement creating/using chatrooms | 2 | User may create chatrooms | F, T | 4 | 4 | Nick, 100%
|  | Design UI for friends list | 2 | Mockup UI for friends tab | F, KA | 2 | 1 | Aidan, 20%. Clark, 20%. Stephen, 20%. Joe, 20%. Nick, 20%
|  | Implement adding friends | 2 | User may add friends by username | F, T, KA | 4 | 0
7 | As a registered user, I want to be able to appear offline so that I won't be disturbed. | Code a profile page for the user | 2 | Mockup UI | F, T, KA | 3 | 0
|  | Design UI to allow user to appear offline | 2 | Get general design ideas | F, KA | 2 | 1 | Aidan, 20%. Clark, 20%. Stephen, 20%. Joe, 20%. Nick, 20%
2
15 | As a registered user, I want to be able to logout of my account at any time so that I can keep my messages secure. | Setup Firebase for handing user authentication | 2 | Authenticate user login/register/logout | NF, T, KA, B | 3 | 3 | Nick, 50%. Clark, 50%
|  | Implement user login | 2 | Allow user to login | F, T | 1 | 1 | Nick, 50%. Stephen, 50%
|  | Implement user logout | 2 | Allow user to logout | F, T, KA | 1 | 1 | Nick, 100%
|  | Fix user registration | 2 | User may create account but can't login | F, B | 1 | 1 | Nick, 33%. Clark, 33%. Stephen 33%
1 | As an unregistered user, I want to be able to view chat rooms near me so that I can talk to people in my community. | Implement creating/using chatrooms | 2 | User may create chatrooms | F, T | 4 | 4 | Nick, 100%
|  | Authenticate user location before registration | 2 | Allow user to see chats in the area before registration | NF, T, KA | 1 | 0
|  | Design UI for homepage | 2 | Mockup UI and get general design ideas | F, KA | 1 | 1 | Aidan, 20%. Clark, 20%. Stephen, 20%. Joe, 20%. Nick, 20%
|  | Code the homepage for users | 2 | Implement homepage for users to access | F, T, KA | 2 | 0
14 | As a registered user, I want to be notified when a new user joins the chat so that I can greet them. | Implement notification in chat when user has joined/left | 2 | Show messages in chat for joining/leaving | F, T, KA | 2 | 0
|  | Update number of users in chatroom | 2 | Show others how many users are in chat | F, T, KA | 1 | 0
|  | Design UI for multiple chatrooms in the area | 2 | Mockup UI / Get design ideas | F, KA | 1 | 1 | Aidan, 20%. Clark, 20%. Stephen, 20%. Joe, 20%. Nick, 20%